## To Do
Group Number: | 9
Group Name: | NormChat
Group Members: | Christian Browning | Sriya Machunuri | Giovanni Abbate | Mina Rao | Jared Hawkins-Young
Product Backlog (TO - DO)
Story # | Front | Back | Sprint # | Priority | Assigned to | Comments | Estimated Points
ST-3 | As a student I need to know specific prerequisite before registration so that I can register for classes easily, avoiding confusion | User should be able to input specific class information into chatbox, output should display class information, filtering redundancy based on specific question | 8 | 8th | Sriya, Jared |  | 6
ST-5 | As a freshman I want to know whats happening around campus so that I can get familiarized | Users should be able to access dynamic links that showcase different events that are happening around campus | 4 | 4th | Jared |  | 5
ST-7 | As a user I want a relevant link with search results. | When a user makes a query the system will return a relevant link when applicable. | 3 | 6th | Sriya, Jared |  | 2
Product Backlog (In Progress)
ST-9 | As a user I want to be able to log in with my email | Users should be able to log in with email | 3 | 3rd |  |  | 2
ST-8 | As a user I want to be able to go back and view past conversations | User should be able to access previous conversations through the conversation list | 3 | 2nd |  |  | 5
Product Backlog (Done) | [5 empty] | Sprint 2
Story# | Card Front | Card Back | Sprint Number | Priority | Estimated Points | Estimated Hours | Actual Hours | Estimated Velocity | Actual Velocity
ST-0 | As a user I want an appealing user interface. | Implement a user interface based on BotSharp UI | 1 | 1st | Christian, Giovanni |  | 5
ST-6 | As a user I want to be able to give feedback to the developers of this tool. | Users should be able to access a form on the site where they can give feedback. | 4 | 7th | Christian |  | 5
ST-2 | As a user I want to be able to find any department on campus | Asking the chat bot for the location of a department will return location to the user | 2 | 3rd | Mina |  | 4
ST-4 | As a student on campus I need to know information about restaurants on campus so that I can get something to eat. | User should be able to prompt chatbox to display location, hours, and other information that matches their search. | 5 | 5th | Jared |  | 5
ST-1 | As a user I want my data to be secure in my account | The user should be able to log in with personal credentials to access their account and saved information. | 1 | 2nd | Giovanni |  | 5